## Gantt Chart
Restaurant Management System Project
Timeline Visualization
Task Name | Week1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Milestone 1: Project Planning & Initiation
Epic 1.1: Project Scope Definition and Planning
Epic 1.2: Initial Project Setup
Milestone 2: Design (UI/UX & Backend Architecture)
Epic 2.1: Design the User Interface for Order Management, Reservations, and Inventory
Epic 2.2: User Interface Testing and Feedback
Epic 2.3: Develop Backend Architecture
Milestone 3: Development (Frontend & Backend)
Epic 3.1: Build Frontend Interface
Epic 3.2: Develop Backend for Order Management, Reservations, and Inventory
Milestone 4: Integration & Testing
Epic 4.1: System Integration (Frontend & Backend)
Epic 4.2: Module Testing (QA)
Epic 4.3: User Acceptance Testing (UAT)
Milestone 5: Final Adjustments, Deployment & Post-Launch
Epic 5.1: Final Adjustments & Optimization
Epic 5.2: System Deployment & Staff Training
Epic 5.3: Post-Launch Support & Monitoring

## WBS Dictionary
WORK BREAKDOWN STRUCTURE
| PROJECT TITLE | PROJECT ID | PROJECT MANAGER |  |  |  | DATE | VERSION
| RestaurantMangement Systems | 1 | [5 empty] | 1.0.0
TASK ID | TASK DESCRIPTION | TASK OWNER | TASK RESOURCES | TASK STATUS | ESTIMATED COST | BEGIN DATE | ESTIMATED DATE OF COMPLETION | ACTUAL DATE OF COMPLETION | ADDITIONAL INFO
1.1 | Project Scope Definition and Planning |  |  | 0% | 0 | January 1, 2025 | January 12, 2025 | -
1.1.1 | Define project scope and objectives | Project Manager (PM) |  | 0% |  |  |  | -
1.1.1.1 | Gather requirements from stakeholders | Project Manager (PM) |  | 0% |  |  |  | -
1.1.1.2 | Define success criteria | Project Manager (PM) |  | 0% |  |  |  | -
1.1.2 | Identify and assign project roles | Project Manager (PM) |  | 0% |  |  |  | -
1.1.2.1 | Assign roles to team members (PM, Team Lead, Developers, etc.) | Project Manager (PM) |  | 0% |  |  |  | -
1.1.2.2 | Create communication plan | Project Manager (PM) |  | 0% |  |  |  | -
1.2 | Initial Project Setup |  |  | 0% | 0 | January 13, 2025 | January 21, 2025 | -
1.2.1 | Set up project management tools (e.g., Jira) | Project Manager (PM) |  | 0% |  |  |  | -
1.2.1.1 | Create project boards and define workflows | Scrum Master |  | 0% |  |  |  | -
1.2.2 | Establish timelines and sprint schedule | Scrum Master |  | 0% |  |  |  | -
2.1 | Design the User Interface for Order Management, Reservations, and Inventory |  |  | 0% | 0 | January 22, 2025 | February 11, 2025 | -
2.1.1 | Research user requirements and workflows | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.1.1 | Interview restaurant staff for workflow insights | Project Manager (PM) |  | 0% |  |  |  | -
2.1.1.2 | Define user personas | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.2 | Create wireframes for key modules | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.2.1 | Wireframe for order management | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.2.2 | Wireframe for reservation system | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.2.3 | Wireframe for inventory tracking | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.3 | Develop interactive prototypes | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.3.1 | Prototype order management screen | UI/UX DESIGNER |  | 0% |  |  |  | -
2.1.3.2 | Prototype reservation system | UI/UX DESIGNER |  | 0% |  |  |  | -
2.2 | User Interface Testing and Feedback |  |  | 0% | #REF! | February 4, 2025 | February 11, 2025 | -
2.2.1 | Conduct usability testing | UI/UX DESIGNER |  | 0% |  |  |  | -
2.2.1.1 | Test interface with restaurant staff | UI/UX DESIGNER |  | 0% |  |  |  | -
2.2.1.2 | Collect and document feedback | UI/UX DESIGNER |  | 0% |  |  |  | -
2.3 | Develop Backend Architecture |  |  | 0% | #REF! | January 22, 2025 | February 11, 2025 | -
2.3.1 | Set up database structure for orders, reservations, and inventory | Database administrator |  | 0% |  |  |  | -
2.3.1.1 | Design ER diagram for database | Database administrator |  | 0% |  |  |  | -
2.3.1.2 | Create database tables for each module | Database administrator |  | 0% |  |  |  | -
2.3.2 | Develop API for order management | Software developer |  | 0% |  |  |  | -
2.3.2.1 | Develop order processing endpoint | Software developer |  | 0% |  |  |  | -
2.3.2.2 | Handle payment processing API integration | Software developer |  | 0% |  |  |  | -
2.3.3 | Implement inventory tracking system | Software developer |  | 0% |  |  |  | -
2.3.3.1 | Build real-time stock management functionality | Software developer |  | 0% |  |  |  | -
3.1 | Build Frontend Interface |  |  | 0% | #REF! | February 12, 2025 | March 3, 2025 | -
3.1.1 | Implement frontend for order management | Software developer |  | 0% |  |  |  | -
3.1.1.1 | Code order entry forms | Software developer |  | 0% |  |  |  | -
3.1.1.2 | Integrate order tracking display | Software developer |  | 0% |  |  |  | -
3.1.2 | Build frontend for reservations | Software developer |  | 0% |  |  |  | -
3.1.2.1 | Develop reservation booking form | Software developer |  | 0% |  |  |  | -
3.1.2.2 | Integrate calendar for reservation tracking | Software developer |  | 0% |  |  |  | -
3.1.3 | Build frontend for inventory tracking | Software developer |  | 0% |  |  |  | -
3.1.3.1 | Create inventory dashboard | Software developer |  | 0% |  |  |  | -
3.1.3.2 | Display real-time stock updates | Software developer |  | 0% |  |  |  | -
3.2 | Develop Backend for Order Management, Reservations, and Inventory |  |  | 0% | #REF! | February 12, 2025 | March 3, 2025 | -
3.2.1 | Connect backend API for order management | Software developer |  | 0% |  |  |  | -
3.2.1.1 | Test order processing functionality | QA Tester |  | 0% |  |  |  | -
3.2.2 | Build backend logic for reservation system | Software developer |  | 0% |  |  |  | -
3.2.2.1 | Develop backend for reservation calendar | Software developer |  | 0% |  |  |  | -
3.2.3 | Integrate inventory tracking with backend system | Software developer |  | 0% | #REF! |  |  | -
3.2.3.1 | Link real-time stock updates to database | Software developer |  | 0% |  |  |  | -
4.1 | System Integration (Frontend & Backend) |  |  | 0% | #REF! | March 4, 2025 | March 9, 2025 | -
4.1.1 | Connect order management API to frontend | Software developer |  | 0% |  |  |  | -
4.1.1.1 | Test API connection with frontend | QA Tester |  | 0% |  |  |  | -
4.1.1.2 | Handle error reporting and handling | QA Tester |  | 0% |  |  |  | -
4.1.2 | Integrate inventory tracking API with frontend dashboard | Software developer |  | 0% |  |  |  | -
4.1.2.1 | Test real-time data syncing | QA Tester |  | 0% |  |  |  | -
4.1.2.2 | Test stock alerts and notifications | QA Tester |  | 0% |  |  |  | -
4.2 | Module Testing (QA) |  |  | 0% | #REF! | March 9, 2025 | March 14, 2025 | -
4.2.1 | Perform unit testing for each module | QA Tester |  | 0% |  |  |  | -
4.2.1.1 | Test order management module | QA Tester |  | 0% |  |  |  | -
4.2.1.2 | Test inventory system functionality | QA Tester |  | 0% |  |  |  | -
4.2.2 | Conduct end-to-end testing for system flow | QA Tester |  | 0% |  |  |  | -
4.2.2.1 | Simulate user journey from order to inventory update | Software developer |  | 0% |  |  |  | -
4.3 | User Acceptance Testing (UAT) |  |  | 0% | #REF! | March 9, 2025 | March 14, 2025 | -
4.3.1 | Prepare UAT environment | QA Tester |  | 0% |  |  |  | -
4.3.1.1 | Set up staging environment | QA Tester |  | 0% |  |  |  | -
4.3.2 | Conduct test cases with restaurant staff | QA Tester |  | 0% |  |  |  | -
4.3.2.1 | Test order placement and fulfillment | QA Tester |  | 0% |  |  |  | -
4.3.2.2 | Test reservation management and booking flow | QA Tester |  | 0% |  |  |  | -
4.3.2.3 | Gather feedback on inventory tracking system | Scrum Master |  | 0% |  |  |  | -
5.1 | Final Adjustments & Optimization |  |  | 0% | #REF! | March 15, 2025 | March 24, 2025 | -
5.1.1 | Optimize database queries | Database administrator |  | 0% |  |  |  | -
5.1.1.1 | Improve query speed for order and inventory updates | Database administrator |  | 0% |  |  |  | -
5.1.2 | Address performance bottlenecks in frontend | Software developer |  | 0% |  |  |  | -
5.1.2.1 | Reduce load times for inventory dashboard | Software developer |  | 0% |  |  |  | -
5.2 | System Deployment & Staff Training |  |  | 0% | #REF! | March 25, 2025 | April 4, 2025 | -
5.2.1 | Deploy system to live environment | Scrum Master |  | 0% |  |  |  | -
5.2.1.1 | Set up production environment | Scrum Master |  | 0% |  |  |  | -
5.2.1.2 | Migrate data from testing to production database | Scrum Master |  | 0% |  |  |  | -
5.2.2 | Train staff on the system | Scrum Master |  | 0% |  |  |  | -
5.2.2.1 | Create training manuals and materials | Scrum Master |  | 0% |  |  |  | -
5.2.2.2 | Provide training on inventory tracking and updates | Scrum Master |  | 0% |  |  |  | -
5.3 | Post-Launch Support & Monitoring |  |  | 0% | #REF! | April 4, 2025 | April 14, 2025 | -
5.3.1 | Monitor system performance | Project Manager (PM) |  | 0% |  |  |  | -
5.3.1.1 | Monitor API and database performance | Project Manager (PM) |  | 0% |  |  |  | -
5.3.1.2 | Track system logs for errors | Scrum Master |  | 0% |  |  |  | -
5.3.2 | Address any reported issues after launch | QA Tester |  | 0% |  |  |  | -
5.3.2.1 | Prioritize bug fixes based on severity | QA Tester |  | 0% |  |  |  | -
- | - |  |  | 0% |  |  |  | -
|  |  | ESTIMATED TOTAL |  | #REF!